This packet is a companion resource for the Comprehensive Literacy State Development (CLSD) professional learning module (PLM) titled “Strategies for Project Sustainability Planning.” The packet’s content follows the project timeline framework in the PLM and offers key considerations, discussion questions, and simple fillable templates that can be used in conjunction with any of the sample resources included in the module.

# CLSD Project Sustainability Planning

Ideally, sustainability planning begins during the CLSD grant application process, but it is never too late to create a plan for continuing a project after grant funding ends. The timeline below provides a suggested breakdown of activities for a long-term sustainability planning approach beginning in Year 1 of project funding. If planning for sustainability is initiated in a later project year, activities from previous years can be combined with activities listed for the current year of funding.

For additional information on sustainability, visit the webpage of the CSLD topical meeting titled “Growing Together: Building Sustainable Literacy Practices.”

Table of Contents

CLSD Project Sustainability Planning	2

Project Year 1: Focus on Developing a CLSD Project Sustainability Plan	4

Establish a CLSD Sustainability Team	4

Review the Project Structure	5

Assess Project Implementation	7

Develop a Sustainability Plan	9

Project Year 2: Focus on Building Relationships	11

Start With Existing Partners	11

Build Relationships and Establish Strategic Partnerships	12

Update the Sustainability Plan	12

Share Successes	13

Project Year 3: Focus on Conducting Outreach	14

Develop Marketing and Outreach Efforts	14

Share the Sustainability Plan	16

Prepare for Future Funding Reductions/Establish a Sustainability Funding Committee	16

Project Year 4: Focus on Securing Funding	18

Review Organizational Capacity	18

Integrate Cost-Effectiveness and Efficiency Strategies	19

Identify Additional or Increased Funding Sources	21

Build New and Mutually Beneficial Partnerships	21

Project Year 5: Focus on Preparing for Project Continuation	23

Prepare for Project Continuation	23

# Project Year 1: Focus on Developing a CLSD Project Sustainability Plan

## Establish a CLSD Sustainability Team

Identify key stakeholders who see value in the program and could help create a sustainability plan for the project. Begin with your project planning/implementation team, and then consider other stakeholders who are vested in the project’s success (e.g., community partners, other agency personnel, families, and district personnel). At least one representative from a subgrantee should also be part of the sustainability team to capture subgrantees’ needs. When establishing a sustainability team, it might be helpful to consider the following questions:

- How could you repurpose or expand existing teams, including the implementation team, to address sustainability?

- How could subgrantees, teachers, staff members, parents, students, and partner organizations be included?

- Are there organizations beyond current partners and collaborators that are passionate about the mission of your project?

You might also find it helpful to complete a roster of potential CLSD sustainability team members, including their organizational affiliations, areas of expertise, and potential roles on the team:

| Member | Organization | Unique Expertise/Experience/Perspective | Role |
| --- | --- | --- | --- |

## Review the Project Structure

Most models for sustainability planning begin with a review of the project’s structure, including the long-term vision, goals, and activities or services provided to achieve those goals. This can aid in framing project elements, as well as prioritizing essential elements for continuation after the grant funding cycle ends. With your CLSD sustainability team, review your application for these foundational elements. A framework may exist in an implementation or evaluation plan. If not, logic models, rubrics, and other tools used in program evaluation might be useful in this process. Some examples are provided in Project Year 1’s “Resources” section. Note that the resources used in Year 1 to establish your plan can also be used in Year 5 to finalize your plan.

If you have an existing logic model for your project, start by looking at resources, which typically include items such as staff members, expertise, in-kind resources, and partnerships, in addition to funding. These are resources you will need to sustain your program after CLSD grant funding ends. Keeping in mind that sustainability planning will happen alongside project implementation, use the project review to inform both. Starting sustainability planning in Year 1 allows you to build sustainability strategies into project activities from the beginning.

Consider the following as you outline your project.

Project Vision and Mission Statements: What are the current mission and vision of your project? Does your mission focus on your target populations? Should this mission remain the same after grant funding ends, or have your target populations’ needs evolved?

| Project Vision Statement |  |
| --- | --- |
| Project Mission Statement |  |
| Target Populations |  |

Populations Served: Whom does your project serve—birth to age 5, kindergarten through grade 5, grades 6 through 12, adults? Where are services provided—schools, communities? Approximately how many of each group currently receive services?

| Population Served | Service Location | Number Served |
| --- | --- | --- |

Primary Project Activities: Review the needs assessment from your grant application. What services does your project provide to support your vision or mission statement? Which grantee or subgrantee needs and program goals do they support? Review any existing logic models or rubrics, or you might wish to complete a table such as the one below:

| Population Served and Priority Need | Project SMART Goal (Specific, Measurable, Achievable, Relevant, Time-Bound) | Activities/Services That Address Project Goals | Outcome Measures and Data Sources |
| --- | --- | --- | --- |

## Assess Project Implementation

An assessment of a CLSD project’s implementation offers an opportunity to look at key programmatic factors that could significantly affect outcomes. In addition, focusing on deepening key areas of implementation known to affect sustainability can help your program target areas for the project’s sustainability early on.

One way to do this is to work with your CLSD sustainability team to examine your project through an Active Implementation Formula lens and determine whether any areas of implementation known to affect sustainability require specific attention. The Active Implementation Formula looks at effective practices—such as evidence-based interventions, effective implementation, outlining the extent to which a practice has been implemented with fidelity, and enabling context, which includes outlying factors such as available school supports—and their combined impact on outcomes. For more information about the Active Implementation Formula, visit the State Implementation and Scaling-up of Evidence-based Practices (SISEP) Center’s Active Implementation Hub.

Active Implementation Formula

(Based on a SISEP Center graphic)

Another tool you might consider is the Program Sustainability Assessment Tool (PSAT). This 40-item questionnaire is a self-assessment tool for evaluating the sustainability capacity of a program. The tool offers a method for rating sustainability across eight key domains. The tool also includes some action-planning guidance and activities to use with your team related to sustainability planning in each of those key areas.

Through strategic planning, grantees can support sustainability at the subgrantee level by considering (1) the effective practices at the subgrantee level, such as program adaptations; (2) the activities included in effective implementation, such as funding stability, communication internally and with stakeholders, and organizational capacity; and (3) how the grantee could help enable and strengthen additional program context, such as partnerships, environmental support, and program evaluation.

## Develop a Sustainability Plan

There are many guides for creating a sustainability plan, with varying numbers of steps and phases. Some example sustainability plans and complementary resources are included in the resources section. The sample sustainability plan steps below include approaches from a range of professional fields. Work with your sustainability team to determine the best fit for your CLSD project. At a minimum, most sustainability plans address the following:

- Sustainability Goals (What your sustainability plan is trying to achieve.)

- Financial Planning (How funding will be allocated to sustain the project.)

- Capacity Building (How resources will be leveraged to fill funding gaps for sustainability.)

- Long-Range Strategic Planning (How sustainability efforts will be broken down over time to enable sustainability plan implementation and success that extends throughout and beyond your grant cycle.

Optional Templates and Plans

In addition to developing a CLSD project sustainability plan at the state level, consider collaborating with subgrantees to develop resources such as:

(a) a sustainability plan template;

(b) a sustainability plan for each subgrantee; or

(c) a combination of the above.

Questions to Consider in Project Year 1

With your CLSD sustainability planning team, consider the following questions to reflect upon in Project Year 1.

- Ideally, which elements would you like to sustain?

- Which program elements must be sustained in order for the project to be viable?

- Which program elements are vital to providing essential services and meeting population needs?

- What staff members are integral to implementing the program at both the grantee level and the subgrantee level? What are their current knowledge gaps, and how could they be filled?

- What resources will be needed for ongoing training of new staff members after grant implementation ends?

- How could you facilitate implementation of systems and processes that would support sustainability within subgrantees by ensuring continuation of knowledge even when staff members change? What technical assistance activities will need to continue, and/or how could technical assistance resources be archived for future staff use?

- Are there services or professional development currently provided by partners or consultants that could be brought in-house by building internal capacity during grant implementation?

# Project Year 2: Focus on Building Relationships

## Start With Existing Partners

CLSD grantees are required to work with specific organizations. For example, a grantee must collaborate with the state agency responsible for administering early childhood education programs and the state agency responsible for administering child care programs in the state, and the grantee can collaborate with the state agencies administering the Part C program for infants and toddlers under the Individuals with Disabilities Education Act or with institutions of higher education.

Different types of partnerships can be viewed as a continuum of levels of engagement, as in the example below:

Himmelman, A. T. (2002). Collaboration for a change: Definitions, decision‐making models, roles, and collaboration process guide. Minneapolis, MN: Himmelman Consulting. https://tennessee.edu/wp-content/uploads/2019/07/Himmelman-Collaboration-for-a-Change.pdf

Consider where your partnerships currently fall on the continuum on the basis of commitments, the degree of change required, the risk involved, the self-sufficiency of each party, power, trust, and willingness to share. With your CLSD sustainability team, determine how you could move partnerships along the continuum toward more secure collaborative or integrated relationships.

If you have not already spoken to your existing partners about what collaboration will look like after grant funding ends, do so now. Define how you will continue to work together and how services could be further integrated over time. Also, review how subgrantees are working with their partners—such as nonprofits, local businesses, and institutions of higher education—to identify areas for improvement.

## Build Relationships and Establish Strategic Partnerships

Building strong relationships with community and project partners can help to ensure their vested interest in your CLSD program’s success and continuation. The relationships you build with other organizations and individuals can connect you to new resources and create champions for the success of your project. Successful partnerships and relationships require a strategic approach.

With your team, discuss establishing and developing new collaborations. As you strategically approach new partners, consider the following:

  - The costs and benefits of establishing a partnership for each party;

  - Creating a shared vision and setting expectations for the partnership;

  - Clearly defining the staff members involved and the contributions they are each expected to make;

  - Making plans for utilizing existing resources from each partner and establishing terms for obtaining shared resources in the future;

  - Paths of communication for each partner; and

  - Outlining how progress will be monitored.

As you begin building relationships and establishing strategic partnerships, think about recruiting members of the community and partner organizations for your sustainability team.

## Update the Sustainability Plan

The sustainability plan is a living document that should be revisited and updated routinely. Once you have completed your partnership review, incorporate your partners into the sustainability plan to reflect additional in-kind or financial resources. The CLSD sustainability team should also update the sustainability plan as needed based on implementation changes or data that have been reported on Government Performance and Results Act (GPRA) measures or program-specific performance measures.

## Share Successes

Sharing CLSD project achievements with stakeholders through stories and statistics is an excellent way to enhance community member and partner buy-in. This can be done through community events or by synthesizing evaluation statistics and presenting milestones and achievements through marketing and outreach efforts, such as your state’s, district’s, or school’s newsletter.

Questions to Consider in Project Year 2

With your CLSD sustainability planning team, consider the following questions to reflect upon in Project Year 2.

- Are all of your existing partnerships functioning well at their current points on the continuum?

- Could any partnerships be expanded to new levels of engagement?

- Are there points along the continuum where new partnerships could fill a gap?

- What could you learn from current partners during implementation that would help both you and your subgrantees build capacity for long-term sustainability?

- Are there partnerships one subgrantee has that could be expanded to other subgrantees? Are there duplicative partnerships that could be consolidated across subgrantees?

# Project Year 3: Focus on Conducting Outreach

## Develop Marketing and Outreach Efforts

A marketing and outreach plan can help build CLSD project visibility and support among important stakeholders, including fellow state, district, or school leaders; policymakers; partners; potential funders; and community members and organizations. Grantee and subgrantee project data—such as results from pre- and post-assessments, participation data, survey feedback, data from subgrantee monitoring, information gained during site visits, and reporting data or analysis from an external evaluator if your project utilizes one—can be used to create materials that highlight project impact and emphasize the importance of continuation.

Review some additional tips for creating marketing and outreach materials:

- Highlight your target audience members and what they care about. Use any relevant data and your knowledge of the stakeholders you serve to tailor outreach. The language, format, and delivery platforms (in person, on paper, and/or virtual) should align with your audience’s needs, interests, and preferences.

- Use catchy titles and subject lines to hook readers. For example, “Five Secrets for Reducing Reading Anxiety” is likelier to capture attention than “Anxiety Reduction Tips.”

- Tell your CLSD project’s story. Use branding (such as your program’s, state’s, or district’s logo), photos, stories, quotations, data, and anecdotes to show and tell readers what your program is doing, how it’s affecting students and others, and why your work makes a difference to individuals and to the entire community.

- Share the spotlight. Feature school districts, individual schools, or particular classrooms displaying innovative practices; current and former students and their family members; school and community partners; volunteers; and special guests who are connected to your program and its goals. Inviting people to contribute is a good way to include diverse voices and keep your content fresh.

- Make your marketing materials visually appealing. Include graphics, icons, and photos that are appropriate, interesting, and relevant to your content and your target audience.

- Use content with permission. If you want to post photos or videos of staff members, family members, or students, be sure to get a signed release form from everyone involved. If you use graphics or photos from outside sources, be sure to use copyright-free images.

- Close with a call to action. A call to action prompts readers to take the next step and act on what they’ve read. This is where you make an ask, big or small, about what resources that group could provide to support CLSD project sustainability. Provide specific steps to secure their commitment.

Sample Infographic

## Share the Sustainability Plan

Use the sustainability plan to build buy-in. Share the long-term vision of the CLSD project and the sustainability strategies with grantee and subgrantee staff members and leadership so they understand that the project has the support needed to continue beyond CLSD grant funding. This will help establish buy-in with the staff members implementing the project, as they will know that their work is seen as critical and that the initiative will be sustained. Ensure subgrantee school board members, administrators, principals, and other leaders understand their role in the sustainability plan so they can also act as key champions for the project.

## Prepare for Future Funding Reductions/Establish a Sustainability Funding Committee

Move toward connecting with new funding sources as you prepare for possible future funding reductions. In addition to your CLSD sustainability team, you might want to establish a sustainability funding committee that could focus solely on identifying and securing new sources of funding.

| Member | Organization | Unique Expertise/Experience/Perspective | Role |
| --- | --- | --- | --- |

You might find it helpful to revisit “Establish a CLSD Sustainability Team” in the “Project Year 1: Focus on Developing a CLSD Project Sustainability Plan” section as you consider how best to establish a sustainability funding committee. It also might be helpful to use the table below to begin selecting members.

Questions to Consider in Project Year 3

With your CLSD sustainability planning team, consider the following questions to reflect upon in Project Year 3.

- Are you including individuals who are familiar with the project’s budget, goals, and core activities and services?

- Are there individuals from partner organizations with experience seeking and securing funding?

# Project Year 4: Focus on Securing Funding

## Review Organizational Capacity

A review of your project’s organizational capacity can help you to align that information with the resources necessary for the continuation of each element. You might find it helpful to revisit your CLSD project’s objectives, the results of your Year 1 project review, and/or your PSAT results. The next step would be to reassess your sustainability goals on the basis of the most recent outcome data available.

A simple SWOT (strengths, weaknesses, opportunities, and threats) analysis can also be useful in kickstarting this process. The following tables are sample formats for conducting a SWOT analysis with your sustainability team.

| Internal Factors |  |
| --- | --- |
| Strengths What does your program do well? What unique resources can you draw on? What do others see as your program’s strengths? | Weaknesses What could your program improve? Where do you have fewer resources than others? What are others likely to see as weaknesses? |
| External Factors |  |
| Opportunities What opportunities, collaborations, and resources are available to your program? How could you turn your strengths into opportunities? | Threats What external variables and forces could have a negative impact on your project? What services or activities are other programs already providing? What threats do your weaknesses expose you to? |

## Integrate Cost-Effectiveness and Efficiency Strategies

Some CLSD grantees may have included prioritizing and addressing cost-effectiveness and efficiency in their grant applications to address sustainability challenges without disrupting programming and may already be implementing these practices. The strategies identified to support these priorities will help streamline funding needs and therefore support sustainability planning. Ensure the sustainability team and the sustainability funding committee know about these strategies, and encourage feedback developed during sustainability planning to increase or enhance those strategies.

Grantees that did not write these priorities in their grant applications can still take a cost-effectiveness and efficiency approach to identify strategies that could be implemented during and after grant funding to facilitate long-term sustainability.

The tools used in the Active Implementation Formula might be helpful in evaluating the fit and feasibility of continuing or modifying aspects of your program. One example, the Hexagon Discussion and Analysis Tool, is illustrated on the next page. This tool includes three program indicators in green (supports, evidence, and usability) and three implementing site indicators in blue (need, capacity, and fit) and can be used to organize feedback and to inform decisions. Use the Hexagon Discussion and Analysis Tool instructions to guide your CLSD sustainability team’s discussion.

Metz, A., & Louison, L. (2018). The Hexagon Tool: Exploring Context. Chapel Hill, NC: National Implementation Research Network, Frank Porter Graham Child Development Institute, University of North Carolina at Chapel Hill. Based on Kiser, Zabel, Zachik, & Smith (2007) and Blase, Kiser, & Van Dyke (2013).

## Identify Additional or Increased Funding Sources

When CLSD program elements are selected for continuation, the identification of resources necessary to sustain these elements can begin. Project Year 4 is the time for a detailed breakdown of the project’s budget, existing resources, and resource gaps that will exist when grant funding ends.

With your CLSD sustainability team, review and discuss the questions listed in the “Questions to Consider in Project Year 4” section. You might also want to revisit the sustainability goals created in your grant application, implementation plan, or sustainability plan and add financial details. It might also be helpful to break down costs at different levels and highlight gaps that will occur when grant funding ends before attempting to identify replacement resources. Consider working with your team to explore additional grant opportunities, maximizing fiscal resources, and the possibility of blending, braiding, or layering funds. If you have established a sustainability funding committee, you will want to include its members in your discussions.

## Build New and Mutually Beneficial Partnerships

As grant funding nears its conclusion, it is time to consider the partnerships and collaborations built so far and ways to leverage these relationships to support program continuation. Meeting with project partners to reflect on strengths and challenges can help determine whether continuing the relationships in the future would be mutually beneficial.

Questions to Consider in Project Year 4

With your CLSD sustainability planning team, consider the following questions to reflect upon in Project Year 4.

- Overall CLSD Program Costs

  - How much does the project currently cost to operate?

  - How has this changed over the course of this funding cycle?

  - Will budget cuts occur in the remaining years of the grant cycle?

- Participant Costs

  - What is the cost of services per student per year? Per month? Per day?

  - Will you continue to serve the same number of students after the grant expires?

  - Will you provide services/activities at the same dosages after the grant expires?

- Activity Costs

  - What is the cost of each program element or activity, including the costs of materials, supplies, other resources, instructors, and fringe benefits?

  - What is the total cost of sustaining a selected set of activities, including the cost for administrative staff members and any overhead costs?

- Current Funding Sources

  - What resources do you currently have that support activities?

  - What percentage of current resources come from grant funding?

- Resource Needs for Sustainability

  - What additional resources will you need to cover costs without grant funding?

  - What resources are allowable under your state’s or district’s guidance?

  - Do the additional resources meet the requirement to supplement and not supplant?

# Project Year 5: Focus on Preparing for Project Continuation

## Prepare for Project Continuation

Review the financial breakdown of costs created in Year 4, and consider updating your capacity assessment to reflect the funding and resources you have secured for the future. Use this information to finalize the components of your project that will continue after grant funding ends, and begin to implement your sustainability plan.

Sustainability planning is an ongoing process. As you approach the end of your grant’s life cycle, you should maintain your sustainability plan as a working document. Sustainability from a dynamic perspective is one such process that considers adaptations or modifications in the implementation process. The process supports building adaptive capacity for stakeholders to make changes on the basis of need.

Your team should finalize the CLSD sustainability plan, which includes determining what program components can be sustained at this time on the basis of secured funding and resources; final program implementation; subgrantee and grantee capacity; and outcome data.

Questions to Consider in Project Year 5

With your CLSD sustainability planning team, consider the following questions to reflect upon in Project Year 5.

- Review the financial breakdown of costs created in Year 4. How has your project’s capacity changed?

- Thinking of the funding and resources you have secured for the future, what components of your project will continue after grant funding ends?

Chambers, D. A., Glasgow, R. E., & Stange, K. C. (2013). The dynamic sustainability framework: Addressing the paradox of sustainment amid ongoing change. Implementation Science, 8, 117. https://doi.org/10.1186/1748-5908-8-117